## Detailed Comms Plan
Pirate360 Foundations Detailed Communications Plan
Area | Timing | Description |  |  | Channel(s) | [7 empty] | Audience
Dept | Target Week/Date | Title of Communication or Activity | Communication Type | Cadence | Email | 1st Monday Newsletter | EMMA | Teams | Survey/Poll | Pirate360 Site / Calendar | Video | Key Messaging | All | People Leaders | Executive Sponsors | Academic Advising/CSS/Academic Success Cohort (SMEs) | Academic Advising/CSS/Academic Success All | Faculty Advising | Experiential Learning Cohort (SMEs) | Experiential Learning All | Academic Advising Demo Attendees | Experiential Learning Demo Attendees | Advising Power Users (Trainers) | Experiential Learning Power Users (Trainers) | Advising Champions | Experiential Learning Champions
Advising | 2025-03-31 | Soft Launch Approach Pt 1 of 3- Why a Softlaunch? | Leadership Messaging | bi-wkly | x | [6 empty] | 1) Reasoning for taking Soft Launch Approcah 2) Soft Launch Benefits 3) Preview of Part 2 | x
Advising | 2025-04-21 | Soft Launch Approach Pt 2 of 3 - How Softlaunch colleges were chosen? | Leadership Messaging | bi-wkly | x | [6 empty] | 1) How and why soft launch colleges were chosen 2) Preview of Part 3 | x
Experiential Learning | 2025-05-12 | Pirate360 Initiative Overview / Website Creation | Leadership Messaging | One-time | x | [6 empty] | 1) Pirate360 initiative overview incl what, why & how 2) Notification of intent to launch a Pirate360 Website for internal stakeholders to self serve | [7 empty] | x
Advising | 2025-05-19 | Soft Launch Approach Pt 3 of 3 - Plan for addressing soft launch implmentation risks | Leadership Messaging | bi-wkly (final) | x | [6 empty] | 1) Plan for addressing raised concerns (release timing and student impact) |  |  |  |  | x
Advising | 2025-06-02 | Champion Network Kickoff | Targeted Messaging | One-time |  |  |  | x |  | x |  | 1) Congratulations on being selected 2) Overview of what a Change Champion means to the implementation and organization 3) Invitation to join | [12 empty] | x
Advising Experiential Learning | 2025-06-02 | PSA - Pirate360 Project Site Launch | Leadership Messaging | One-time | x | [6 empty] | 1) Announce live site 2) What can be found 3) Where to find | x
Advising | 2025-06-16 | Champion Huddle Crib Sheet | Targeted Messaging | bi-wkly |  |  |  | x |  |  |  | 1) Cheat sheet to help Champions relay Project information 2) Messaging / Milestones / Activities | [12 empty] | x
Advising | 2025-06-23 | Leadership Change Advocacy Coaching | Leadership Messaging | One-time |  |  |  | x |  |  |  | 1) Overview of a Change Advocate 2) Roles of an advocate as a People Leader 3) Pitfalls 4) How to lead team through change |  | x
Advising Experiential Learning | 2025-06-23 | WIIFMs Spotlights #1 | Targeted Messaging | Bi-wkly |  |  | x |  |  | x |  | 1) Per message map, graphical spotlights highlighting realized benefits
Advising | 2025-06-30 | Champion Huddle Crib Sheet | Targeted Messaging | bi-wkly |  |  |  | x |  |  |  | 1) Cheat sheet to help Champions relay Project information 2) Messaging / Milestones / Activities | [12 empty] | x
Advising | 2025-06-30 | June Project Update | Project Update | Mthly |  |  | x |  |  | x |  | 1) Timeline 2) Highlights 3) FAQs | x
Experiential Learning | 2025-06-30 | June Project Update | Project Update | Mthly |  |  | x |  |  | x |  | 1) Timeline 2) Highlights 3) FAQs | x
Experiential Learning | 2025-07-07 | Champion Program Selection Notification | Targeted Messaging | One-time | x | [6 empty] | 1)Selection notfication 2) Congratulations on being selected 3) Overview of what a Change Champion means to the implementation and organization 4) Intent to schedule Program Kickoff | [13 empty] | x
Advising Experiential Learning | 2025-07-07 | WIIFMs Spotlights #2 | Targeted Messaging | Bi-wkly |  |  | x |  |  | x |  | 1) Per message map, graphical spotlights highlighting realized benefits
Advising | 2025-07-14 | Champion Huddle Crib Sheet | Targeted Messaging | bi-wkly |  |  |  | x |  |  |  | 1) Cheat sheet to help Champions relay Project information 2) Messaging / Milestones / Activities | [12 empty] | x
Experiential Learning | 2025-07-14 | Leadership Change Advocacy Coaching | Leadership Messaging | One-time |  |  |  | x |  |  |  | 1) Overview of a Change Advocate 2) Roles of an advocate as a People Leader 3) Pitfalls 4) How to lead team through change |  | x
Advising | 2025-07-14 | Sentiment Check | Functional | One time | [7 empty] | 1) Purpose (How are we doing) |  |  |  |  | x
Experiential Learning | 2025-07-21 | Champion Network Kickoff | Targeted Messaging | One-time |  |  |  | x |  | x |  | 1) Congratulations on being selected 2) Overview of what a Change Champion means to the implementation and organization 3) Invitation to join | [13 empty] | x
Advising | 2025-07-21 | July Project Update | Project Update | Mthly |  |  | x |  |  | x |  | 1) Timeline 2) Highlights 3) FAQs | x
Experiential Learning | 2025-07-21 | July Project Update | Project Update | Mthly |  |  | x |  |  | x |  | 1) Timeline 2) Highlights 3) FAQs | x
Advising | 2025-07-28 | Champion Huddle Crib Sheet | Targeted Messaging | bi-wkly |  |  |  | x |  |  |  | 1) Cheat sheet to help Champions relay Project information 2) Messaging / Milestones / Activities | [12 empty] | x
Advising Experiential Learning | 2025-07-28 | WIIFMs Spotlights #3 | Targeted Messaging | Bi-wkly |  |  | x |  |  | x |  | 1) Per message map, graphical spotlights highlighting realized benefits
Experiential Learning | 2025-08-06 | Champion Huddle Crib Sheet | Targeted Messaging | bi-wkly |  |  |  | x |  |  |  | 1) Cheat sheet to help Champions relay Project information 2) Messaging / Milestones / Activities | [13 empty] | x
Advising | 2025-08-11 | Champion Huddle Crib Sheet | Targeted Messaging | bi-wkly |  |  |  | x |  |  |  | 1) Cheat sheet to help Champions relay Project information 2) Messaging / Milestones / Activities | [12 empty] | x
Advising Experiential Learning | 2025-08-11 | WIIFMs Spotlights #4 | Targeted Messaging | Bi-wkly |  |  | x |  |  | x |  | 1) Per message map, graphical spotlights highlighting realized benefits
Experiential Learning | 2025-08-18 | Champion Huddle Crib Sheet | Targeted Messaging | bi-wkly |  |  |  | x |  |  |  | 1) Cheat sheet to help Champions relay Project information 2) Messaging / Milestones / Activities | [13 empty] | x
Experiential Learning | 2025-08-18 | Sentiment Check | Functional | One time | [7 empty] | 1) Purpose (How are we doing) | [7 empty] | x
Advising | 2025-08-25 | August Project Update | Project Update | Mthly |  |  | x |  |  | x |  | 1) Timeline 2) Highlights 3) FAQs | x
Experiential Learning | 2025-08-25 | August Project Update | Project Update | Mthly |  |  | x |  |  | x |  | 1) Timeline 2) Highlights 3) FAQs | x
Advising | 2025-08-25 | Champion Huddle Crib Sheet | Targeted Messaging | bi-wkly |  |  |  | x |  |  |  | 1) Cheat sheet to help Champions relay Project information 2) Messaging / Milestones / Activities | [12 empty] | x
Advising | 2025-08-25 | Go Live Virtual Q&A | Functional | One-time |  |  |  | x |  | x |  | 1) Open venue to relay Go Live info 2) address Go Live related questions | x
Advising Experiential Learning | 2025-08-25 | WIIFMs Spotlights #5 | Targeted Messaging | Bi-wkly |  |  | x |  |  | x |  | 1) Per message map, graphical spotlights highlighting realized benefits
Experiential Learning | 2025-09-01 | Champion Huddle Crib Sheet | Targeted Messaging | bi-wkly |  |  |  | x |  |  |  | 1) Cheat sheet to help Champions relay Project information 2) Messaging / Milestones / Activities | [13 empty] | x
Advising | 2025-09-08 | Go Live Message #1 (week 1) | Leadership Messaging | One Time | x |  |  |  |  | x |  | 1) Inform users of Support Hours & L&Ls 2) Provide L&L schedule including topics, dates, times & facilitators 3) Support contacts |  |  |  |  | x
Advising Experiential Learning | 2025-09-08 | WIIFMs Spotlights #6 | Targeted Messaging | Bi-wkly |  |  | x |  |  | x |  | 1) Per message map, graphical spotlights highlighting realized benefits
Experiential Learning | 2025-09-15 | Champion Huddle Crib Sheet | Targeted Messaging | bi-wkly |  |  |  | x |  |  |  | 1) Cheat sheet to help Champions relay Project information 2) Messaging / Milestones / Activities | [13 empty] | x
Advising | 2025-09-15 | Go Live Message #2 (week 2) | Leadership Messaging | One Time | x |  |  |  |  | x |  | 1) Quotes & Success Stories 2) Support/ Q&A session 3) Tips & Tricks 4) How to Provide Feedback |  |  |  |  | x
Advising | 2025-09-22 | Go Live Message #3 (week 3) | Leadership Messaging | One Time | x |  |  |  |  | x |  | 1) Quotes & Success Stories 2) Support/ Q&A session 3) Tips & Tricks 4) Follow-on support 5) How to Provide Feedback |  |  |  |  | x
Experiential Learning | 2025-09-22 | REMINDER - TTT Detailed Instructions | Functional | One-time | x | [6 empty] | 1) Brief Overview 2) Training what, when, where, why 3) Pre-work required, if any (e.g. Trailheads) 4) Info on training sandbox credentials | [11 empty] | x
Advising | 2025-09-22 | September Project Update | Project Update | Mthly |  |  | x |  |  | x |  | 1) Timeline 2) Highlights 3) FAQs | x
Experiential Learning | 2025-09-22 | September Project Update | Project Update | Mthly |  |  | x |  |  | x |  | 1) Timeline 2) Highlights 3) FAQs | x
Advising Experiential Learning | 2025-09-22 | WIIFMs Spotlights #7 | Targeted Messaging | Bi-wkly |  |  | x |  |  | x |  | 1) Per message map, graphical spotlights highlighting realized benefits
Experiential Learning | 2025-10-06 | Champion Huddle Crib Sheet | Targeted Messaging | bi-wkly |  |  |  | x |  |  |  | 1) Cheat sheet to help Champions relay Project information 2) Messaging / Milestones / Activities | [13 empty] | x
Experiential Learning | 2025-10-06 | Go Live Virtual Q&A | Functional | One-time |  |  |  | x |  | x |  | 1) Open venue to relay Go Live info 2) address Go Live related questions | x
Advising Experiential Learning | 2025-10-06 | WIIFMs Spotlights #8 | Targeted Messaging | Bi-wkly |  |  | x |  |  | x |  | 1) Per message map, graphical spotlights highlighting realized benefits
Advising | 2025-10-13 | 30 Day User Satisfaction Pulse Check | Functional | One Time |  |  |  |  | x |  |  | 1) Survey purpose (How are we doing, user experience feedback, etc.) 2) Call to action (survey link) 3) Survey timeline 4) Appreciation |  |  |  |  | x
Advising | 2025-10-27 | October Project Update | Project Update | Mthly |  |  | x |  |  | x |  | 1) Timeline 2) Highlights 3) FAQs | x
Experiential Learning | 2025-10-27 | October Project Update | Project Update | Mthly |  |  | x |  |  | x |  | 1) Timeline 2) Highlights 3) FAQs | x
Advising | 2026-02-28 | Post secondary User Launch 30-Day Satisfaction Survey | Functional | One Time |  |  |  |  | x |  |  | 1) Survey purpose (How are we doing, user experience feedback, etc.) 2) Call to action (survey link) 3) Survey timeline 4) Appreciation |  |  |  |  | x
Advising | 2026-03-31 | Post secondary User Launch 60-Day Satisfaction Survey | Functional | One Time |  |  |  |  | x |  |  | 1) Survey purpose (How are we doing, user experience feedback, etc.) 2) Call to action (survey link) 3) Survey timeline 4) Appreciation |  |  |  |  | x
Experiential Learning | TBD | 30 Day User Satisfaction Pulse Check | Functional | One Time |  |  |  |  | x |  |  | 1) Survey purpose (How are we doing, user experience feedback, etc.) 2) Call to action (survey link) 3) Survey timeline 4) Appreciation | [7 empty] | x
Experiential Learning | TBD | 60 Day User Satisfaction Pulse Check | Functional | One Time |  |  |  |  | x |  |  | 1) Survey purpose (How are we doing, user experience feedback, etc.) 2) Call to action (survey link) 3) Survey timeline 4) Appreciation | [7 empty] | x
Experiential Learning | TBD | 90 Day User Satisfaction Pulse Check | Functional | One Time |  |  |  |  | x |  |  | 1) Survey purpose (How are we doing, user experience feedback, etc.) 2) Call to action (survey link) 3) Survey timeline 4) Appreciation | [7 empty] | x
Experiential Learning | TBD | Go Live Message #1 (week 1) | Leadership Messaging | One Time | x |  |  |  |  | x |  | 1) Inform users of Support Hours & L&Ls 2) Provide L&L schedule including topics, dates, times & facilitators 3) Support contacts | x
Experiential Learning | TBD | Go Live Message #2 (week 2) | Leadership Messaging | One Time | x |  |  |  |  | x |  | 1) Quotes & Success Stories 2) Support/ Q&A session 3) Tips & Tricks 4) How to Provide Feedback | x
Experiential Learning | TBD | Go Live Message #3 (week 3) | Leadership Messaging | One Time | x |  |  |  |  | x |  | 1) Quotes & Success Stories 2) Support/ Q&A session 3) Tips & Tricks 4) Follow-on support 5) How to Provide Feedback | x

## Standing Meetings
College/Dept/Role | Meeting Title | Meeting Description/Audience | Meeting Owner | Cadence |  |  |  |  | Next Meeting Date
|  |  |  | Wkly | Bi-Wkly | Mthly | Quarterly | Other (fill in) | Meeting Date
COE | College Council Meeting | Dept Chairs, Directors, Dean Suite, Community Schools
Undergraduate Council
Staff Senate
Faculty Senate
| Office for Faculty Excellence |  | Sarah Williams
Student Affairs | Opening Celebration Kickoff Mtg | SA Staff | [6 empty] | End of August
Faculty Convocation
| Professional Development Committee | Reps | Brian Mattern
Provost Council
Institutional Research Office (IPAR)
| Directors Assembly | [7 empty] | Twice a semester